## Version_Control
WORM Subject Planner
Requirements Traceability Matrix

Submitted to:	Ma. Rowena C. Solamo
	Faculty Member
	Department of Computer Science
	College of Engineering
	University of the Philippines, Diliman

Submitted by:	Camba, Jannieca P.
	Domingo, Patrick Leiniel H.
	Jimenez, Joni Marie E.

In partial fulfillment of Academic Requirements
for the course
CS 191 Software Engineering
1st Sem AY 2014-2015

History Revision:

Revision Date	Person Responsible	Version Number	Modification
01/22/15	Camba, Jannieca P.	1.1	Prioritized requirements traceability matrix
	Domingo, Patrick Leiniel H.
	Jimenez, Joni Marie E.
2/13/2015	Domingo, Patrick Leiniel H.	1.2	Adjusted according to sprint 1 results
03/01/15	Domingo, Patrick Leiniel H.	1.3	Adjusted according to sprint 2 results

## Requirements
				Requirements Phase				Design Phase
RTM ID	Description	Scenarios	Priority Status	Has Prototype?	Boundary Class	Control Class	Entity Class	UI Design	Controller Design	Data Design	Story Points	Value Point	BFTB
Subject Use Case 1.1	View subjects	S1: Successful view	Must Have	Yes	Yes	No	Yes	Yes	No	Yes	1	8	8
		S2: Cannot view	Must Have	Yes	Yes	No	Yes	Yes	No	Yes
Subject Use Case 1.0	Create subject	S1: Successful add	Must Have	Yes	Yes	No	Yes	Yes	No	Yes	3	9	3
		S2: Empty title	Must Have	Yes	Yes	No	Yes	Yes	No	Yes
		S3: Subject title already exists	Must Have	No	No	No	No	No	No	No
Notes Use Case 1.0	Create notes	S1: Successful add	Must Have	Yes	Yes	No	Yes	Yes	No	Yes	3	9	3
		S2: Empty title	Must Have	Yes	Yes	No	Yes	Yes	No	Yes
		S3: Note title already exists	Must Have	Yes	Yes	No	Yes	Yes	No	Yes
Notes Use Case 1.1	View Notes	S1: Successful view	Must Have	Yes	Yes	No	Yes	Yes	No	Yes	1	8	8
		S2: Cannot view	Must Have	Yes	Yes	No	Yes	Yes	No	Yes
Subject Use Case 3.0	Delete subject	S1: Successful delete	Must Have	No	Yes	Yes	Yes	No	No	No	2	7	3.5
		S2: Canceled delete	Must Have	No	No	No	No	No	No	No
Notes Use Case 3.0	Delete notes	S1: Successful delete	Must Have	No	Yes	Yes	Yes	No	No	No	2	7	3.5
		S2: Canceled delete	Must Have	No	No	No	No	No	No	No
		S3: Cannot delete	Must Have	No	No	No	No	No	No	No
Subject Use Case 2.0	Edit subject title	S1: Successful edit	Must Have	No	Yes	Yes	Yes	No	No	No	4	6	1.5
		S2: Cannot edit	Must Have	No	No	No	No	No	No	No
		S3: Changed to an empty title	Must Have	No	No	No	No	No	No	No
Notes Use Case 2.0	Edit note title	S1: Successful edit	Must Have	No	Yes	Yes	Yes	No	No	No	4	6	1.5
		S2: Changed to an empty title	Must Have	No	Yes	Yes	Yes	No	No	No
		S3: Changed to an existing title	Must Have	No	Yes	Yes	Yes	No	No	No
Notes Use Case 2.1	Edit note content	S1: Successful edit	Must Have	No	Yes	Yes	Yes	No	No	No	5	5	1
		S2: Cannot edit	Must Have	No	No	No	No	No	No	No
Calendar Use Case 3.1	Add new activity	S1: Successful add	Must Have	No	No	Yes	Yes	No	No	No	7	9	1.2857142857
		S2: Cannot add	Must Have	No	No	No	No	No	No	No
		S3: Adding existing activity	Must Have	No	No	No	No	No	No	No
Calendar Use Case 2.0	View individual activity	S1: Successful view	Must Have	No	Yes	Yes	Yes	No	No	No	7	8	1.1428571429
		S2: Cannot view	Must Have	No	No	No	No	No	No	No
Calendar Use Case 3.3	Delete existing activity	S1: Successful delete	Must Have	No	No	Yes	Yes	No	No	No	7	7	1
		S2: Cannot delete	Must Have	No	No	No	No	No	No	No
Calendar Use Case 1.2	View day activities	S1: Successful view	Must Have	No	Yes	Yes	Yes	No	No	No	6	5	0.8333333333
		S2: Cannot view	Must Have	No	No	No	No	No	No	No
Calendar Use Case 1.1	View month activities	S1: Successful view	Must Have	No	Yes	Yes	Yes	No	No	No	9	7	0.7777777778
		S2: Cannot view	Must Have	No	No	No	No	No	No	No
Calendar Use Case 3.2	Edit existing activity	S1: Successful edit	Must Have	No	No	Yes	Yes	No	No	No	8	6	0.75
		S2: Cannot edit	Must Have	No	No	No	No	No	No	No

Calendar-related

Interface Customization
Interface Use Case 1.1	Choose from themes	S1: Successful selection	Nice to have	No	Yes	Yes	Yes	No	No	No
		S2: Cannot change theme	Nice to have	No	No	No	No	No	No	No

Subject-related
		S3: Cannot delete	Must Have	No	No	No	No	No	No	No
Subject Use Case 4.0	Arrange subject title	S1: Successful arrange	Could Have	No	Yes	Yes	Yes	No	No	No
		S2: Cannot arrange	Could Have	No	No	No	No	No	No	No
Subject Use Case 4.1	Find subject	S1: Successful find	Could Have	No	Yes	Yes	Yes	No	No	No
		S2: Cannot found	Could Have	No	No	No	No	No	No	No
Subject Use Case 4.2	Find notes within the subject	S1: Successful find	Could Have	No	Yes	Yes	Yes	No	No	No
		S2: Cannot found	Could Have	No	No	No	No	No	No	No

Notes-related
Notes Use Case 4.0	Arrange notes	S1: Successful arrange	Could Have	No	Yes	Yes	Yes	No	No	No
		S2: Cannot arrange	Could Have	No	No	No	No	No	No	No

Notes Use Case 5.0	Move notes	S1: Successful move	Nice to have	No	No	No	No	No	No	No
		S2: Cannot move	Nice to have	No	No	No	No	No	No	No
Notes Use Case 5.1	Copy notes	S1: Successful copy	Nice to have	No	No	No	No	No	No	No
		S2: Cannot copy	Nice to have	No	No	No	No	No	No	No
Notes Use Case 5.2	Paste notes	S1: Successful paste	Nice to have	No	No	No	No	No	No	No
		S2: Cannot paste	Nice to have	No	No	No	No	No	No	No
Notes Use Case 5.3	Find words within the note	S1: Successful find	Nice to have	No	No	No	No	No	No	No
		S2: Cannot find	Nice to have	No	No	No	No	No	No	No

Taks-related
Task Use Case 1.0	Search Task	S1: Successful search	Should Have	No	No	No	No	No	No	No
		S2: Cannot find	Should Have	No	No	No	No	No	No	No
Task Use Case 2.0	View Task	S1: Successful view	Should Have	No	No	No	No	No	No	No
		S2: Cannot view	Should Have	No	No	No	No	No	No	No
Task Use Case 2.1	Arrange Task	S1: Successful arrange	Should Have	No	No	No	No	No	No	No
		S2: Cannot arrange	Should Have	No	No	No	No	No	No	No
Task Use Case 3.0	Manage Task
Task Use Case 3.1	Create Task	S1: Successful add	Should Have	No	No	No	No	No	No	No
		S2: Cannot add	Should Have	No	No	No	No	No	No	No
Task Use Case 3.2	Delete Task	S1: Successful delete	Should Have	No	No	No	No	No	No	No
		S2: Cannot delete	Should Have	No	No	No	No	No	No	No
Task Use Case 3.3	Edit Task	S1: Successful edit	Should Have	No	No	No	No	No	No	No
		S2: Cannot edit	Should Have	No	No	No	No	No	No	No